## Sheet1
Test Case ID | Test Case Description (This is one of the bullet points in the report "Functions / Test Cases being targeted") | Created By | Reviewed By | Tester's name | Date Tested | Card (1 or 2) | SUT | Test Function | Intital State | Steps to Reproduce Defect | Expected Outcome | Actual Outcome | Priority (Low, medium, high, Critical) | Severity (Low, medium, high, Critical) | Status of Bug after regression test | Environment | Type of testing the bug was found in
DR-1 | Test invalid inputs for options displayed | Gi-E Thang | Gi-E Thang | Gi-E Thang | 2024-02-04 | 1 | V1.0 | Inputing numbers number options that are not on the listed options | Any state that has number options | Turn on ATM, Enter a number of bills (eg.10) and click return, Click insert card, Enter card number 1, Enter pin 42, Select 0,5,6,7,8 or 9. Since there is multiple cases for this bug, we provided a single example. | Invaild input or does nothing | Freezes the ATM depending on how many times you clicked an option not on the tracntions type. The more you click, the longer the ATM freezes. | Low | Medium | RESOLVED | MacOS | Exploratory Testing
DR-2 | Test invalid inputs for options displayed | Yaad Sra | Yaad Sra | Yaad Sra | 2024-02-04 | 2 | V1.0 | Inputing numbers number options that are not on the listed options | Any state that has number options | Turn on ATM, Enter a number of bills (eg.10) and click return, Click insert card, Enter card number 2, Enter pin 1234, Select 0,5,6,7,8 or 9. Since there is multiple cases for this bug, we provided a single example. | Invaild input or does nothing | Freezes the ATM depending on how many times you clicked an option not on the tracntions type. The more you click, the longer the ATM freezes. | Low | Medium | RESOLVED | MacOS | Exploratory Testing
DR-3 | Cash withdrawal from all accounts linked to card | Andrew Lee | Andrew Lee | Andrew Lee | 2024-02-04 | 2 | V1.0 | withdrawing money | Log in to main menu | Insert card, withdraw money, press 1) for checking account, press 5) $200: wrong output as it only withdraws $20 instead of $200. | Withdraw $200. | Withdraw $20 | High | High | RESOLVED | MacOS | Exploratory Testing
DR-4 | Cash withdrawal from all accounts linked to card | Gi-E Thang | Gi-E Thang | Gi-E Thang | 2024-02-04 | 1 | V1.0 | Cash withdrawal from the money market | ATM money market option | Turn on ATM, Enter a number of bills (eg.10) and click return, Click insert card, Enter card number 1, Enter pin 42, Choose withdrawal, Choose Money Market, Choose 1. | Withdrawal of one 20$ from the money market | Shows a screen for invalid account type | Medium | Medium | RESOLVED | MacOS | Exporatory testing
DR-5 | Cash withdrawal from all accounts linked to card | Gi-E Thang | Gi-E Thang | Gi-E Thang | 2024-02-04 | 1 | V1.0 | Cash withdrawal from the money market | ATM money market option | Turn on ATM, Enter a number of bills (eg.10) and click return, Click insert card, Enter card number 1, Enter pin 42, Choose withdrawal, Choose Money Market, Choose 1. | Withdrawal of one 20$ from the money market | Spelling error for "wood and should be "would" | Low | Low | RESOLVED | MacOS | Exporatory testing
DR-6 | Transfers between accounts linked to card | Gi-E Thang | Gi-E Thang | Gi-E Thang | 2024-02-04 | 1 | V1.0 | Money transfers from chequing to savings | Money transfer option state | Turn on ATM, Enter a number of bills (eg.10) and click return, Click insert card, Enter card number 1, Enter pin 42, Choose transfer, choose from chequing, choose to savings | Transfers a specified amount from chequing to savings | Shows insuffcient amount when there is enough money in the chequings. | Critical | Medium | RESOLVED | MacOS | Exporatory testing
DR-7 | Balance inquiry for all accounts linked to the card | Gi-E Thang | Gi-E Thang | Gi-E Thang | 2024-02-04 | 1 | V1.0 | Checking the balance of the money market | Balance inqury for the money market | Turn on ATM, Enter a number of bills (eg.10) and click return, Click insert card, Enter card number 1, Enter pin 42, Choose balance inquiry, choose money market | Shows the correct balance on the screen | Shows an incorrect number on the screen compared to the reciept as well as it shows an "unknown error" on the screen. | Medium | Medium | RESOLVED | MacOS | Exploratory testing
DR-8 | Balance inquiry for all accounts linked to the card | Gi-E Thang | Gi-E Thang | Gi-E Thang | 2024-02-04 | 1 | V1.0 | Checking the balance in the savings | Account to inquire from | Turn on ATM, Enter a number of bills (eg.10) and click return, Click insert card, Enter card number 1, Enter pin 42, Choose balance inquiry | Have the option to check the balance for the savings | Shows no options to check for the balance in the savings | Critical | Low | RESOLVED | MacOS | Exploatory testing
DR-9 | Cash deposit to all accounts linked to the card | Dillon Pullano | Dillon Pullano | Dillon Pullano | 2024-02-04 | 1 | V1.0 | Deposit into checking account | ATM set up with $1000 in it. Successfully log into account with 'card 1' | Select '2' to Deposit. Select '1' for checking. type 800.00 and hit enter. Click to insert envelope | Reciept shows that total checking balance is $900 and there is $100 available to be withdrawn | Reciept shows that total checking balance is $890 and there is $100 available to be withdrawn | Critical | Critical | IN-PROGRESS (deposit is always 0.10 Lower that the amount and in the high level design, there should be no fee because the high lvel design does not mention it) | Windows 11 | Exporatory testing
DR-10 | Clearing Log | Yaad Sra | Yaad Sra | Yaad Sra | 2024-02-04 | 2 | V1.0 | Withdraw $40.00 then try to clear log | Withdraw $40.00 from Card 2 Checkings account | Successfully withdraw $40.00, then check log to confirm it is logged, then 'clear log' | Log to be cleared, reciept to track all actions correctly | Log is cleared as expected, 2 problems noted: Reciept tracks card as card #3 which is incorrect. Final message has a typo "Wood you like to do another transaction" | High | High | IN-PROGRESS (defect still exists in V1.1) | MacOS | Exploratory testing
DR-11 | System Startup | Group 1 | Group 1 | Group 1 | 2024-02-04 | 1 | V1.0 | Connection to the bank is established | System has just been turned on | Perform a legitimate inquiry transaction | System output should demonstrate that a connection has been established to the Bank | There was no "connection" message. We assume it connected | Low | Medium | IN-PROGRESS (defect still exists in V1.1) | MacOS | Manual Scripted Testing
DR-12 | Session | Group 1 | Group 1 | Group 1 | 2024-02-04 | 1 | V1.0 | System rejects an unreadable card | System is on and not servicing a customer | Insert an unreadable card | Card is ejected; System displays an error screen; System is ready to start a new session | Rejects card names that have letters but accepts numerical cards that are not readable | Medium | Medium | RESOLVED | MacOS | Manual Scripted Testing
DR-13 | Withdrawal | Group 1 | Group 1 | Group 1 | 2024-02-04 | 1 | V1.0 | System asks customer to choose an account to withdraw from | Menu of account types is being displayed | Choose Withdrawal transaction | System displays a menu of possible withdrawal amounts | It shows accounts "money market" where it should only show checking and savings accounts | High | High | IN-PROGRESS (still shows money market in V1.1) | MacOS | Manual Scripted Testing
DR-14 | Withdrawal | Group 1 | Group 1 | Group 1 | 2024-02-04 | 1 | V1.0 | System performs a legitimate withdrawal transaction properly | System is displaying the menu of withdrawal amounts | Choose an amount that the system currently has and which is not greater than the account balance | System dispenses this amount of cash; System prints a correct receipt showing amount and correct updated balance; System records transaction correctly in the log (showing both message to the bank and approval back) | The wrong amount was withdrawn. We selected 20 and it withdrew 40. Wrong amounts are being withdrawn | Critical | Critical | RESOLVED | MacOS | Manual Scripted Testing
DR-15 | Deposit | Group 1 | Group 1 | Group 1 | 2024-02-04 | 1 | V1.0 | System performs a legitimate deposit transaction properly | System is requesting that customer insert an envelope | Insert an envelope | System accepts envelope; System prints a correct receipt showing amount and correct updated balance; System records transaction correctly in the log (showing message to the bank, approval back, and acceptance of the envelope) | Balance is incorrect. We started with 100 and deposited 100. It should show 200 but shows 190 | Critical | Critical | RESOLVED | MacOS | Manual Scripted Testing
DR-16 | Transfer | Group 2 | Group 2 | Group 2 | 2024-02-04 | 1 | V1.0 | System performs a legitimate transfer transaction properly | System is displaying a request for the customer to type a dollar amount | Enter a legitimate dollar amount | System prints a correct receipt showing amount and correct updated balance; System records transaction correctly in the log (showing both message to the bank and approval back) | It added the wrong amount but the numbers worked out for total (given the wrong value was added). We deposited 10 but it only deposited 9.50 (correctly) | Critical | Critical | IN-PROGRESS (still in V1.1) | MacOS | Manual Scripted Testing
DR-17 | Inquiry | Group 2 | Group 2 | Group 2 | 2024-02-04 | 1 | V1.0 | System asks customer to choose an account to inquire about | Menu of transaction types is being displayed | Choose Inquiry transaction | System displays a menu of account types | Checking is shown but savings is not. Instead money market is shown and there is not a money market with this card | High | High | RESOLVED | MacOS | Manual Scripted Testing
DR-18 | Invalid PIN Extension | Group 2 | Group 2 | Group 2 | 2024-02-04 | 1 | V1.0 | Correct re-entry of PIN is accepted | Request to re-enter PIN is being displayed | Enter correct PIN | Original transaction completes successfully | If incorrect the first time, you need to correctly enter it twice to actually log in | Medium | Low | IN-PROGRESS (still in V1.1) | MacOS | Manual Scripted Testing
DR-19 | Invalid PIN Extension | Group 2 | Group 2 | Group 2 | 2024-02-04 | 1 | V1.0 | Correct re-entry of PIN on the second try is accepted | Request to re-enter PIN is being displayed | Enter incorrect PIN the first time, then correct PIN the second time | Original transaction completes successfully | If incorrect the first time, you need to correctly enter it twice to actually log in | Medium | Low | IN-PROGRESS (still in V1.1) | MacOS | Manual Scripted Testing
DR-20 | Invalid PIN Extension | Group 2 | Group 2 | Group 2 | 2024-02-04 | 1 | V1.0 | Correct re-entry of PIN on the third try is accepted | Request to re-enter PIN is being displayed | Enter incorrect PIN the first time and second times, then correct PIN the third time | Original transaction completes successfully | It was on the fourth but it did not lock us on the 3rd time when we typed it correctly. | Medium | Low | RESOLVED | MacOS | Manual Scripted Testing
DR-21 | Cash withdrawal from all accounts linked to card | Gi-E Thang | Gi-E Thang | Gi-E Thang | 2024-02-04 | 1 | V1.1 | withdrawing money | Log in to main menu | Insert card, withdraw money, press 1 for checking account | Seeing all the cash withdrawal properly | The 60 dollar withdrawal is missing a $ sign beside it | Low | Low | IN-PROGRESS | MacOS | Regression Testing
Initial Manual Testing (Below)
<-- test case is completed without defect
1 | System Startup | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System is started when the switch is turned "on" | [8 empty] | Manual Scripted Testing
2 | System Startup | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System accepts initial cash amount | [8 empty] | Manual Scripted Testing
3 | System Startup | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | Connection to the bank is established |  |  |  | There was no "connection" message. We assume it connected |  |  |  |  | Manual Scripted Testing
4 | System Shutdown | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System is shut down when the switch is turned “off" | [8 empty] | Manual Scripted Testing
5 | Session | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System reads a customer's ATM card | [8 empty] | Manual Scripted Testing
6 | Session | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System rejects an unreadable card |  |  |  | Rejects card names that have letters but accepts numerical cards that are not readable |  |  |  |  | Manual Scripted Testing
7 | Session | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System accepts customer's PIN | [8 empty] | Manual Scripted Testing
8 | Session | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System alLows customer to perform a transaction | [8 empty] | Manual Scripted Testing
9 | Session | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System alLows multiple transactions in one session | [8 empty] | Manual Scripted Testing
10 | Session | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | Session ends when customer chooses not to do another transaction | [8 empty] | Manual Scripted Testing
11 | Transaction | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System handles an invalid PIN properly | [8 empty] | Manual Scripted Testing
12 | Withdrawal | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System asks customer to choose an account to withdraw from |  |  |  | It shows accounts "money market" where it should only show checking and savings accounts |  |  |  |  | Manual Scripted Testing
13 | Withdrawal | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System asks customer to choose a dollar amount to withdraw | [8 empty] | Manual Scripted Testing
14 | Withdrawal | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System performs a legitimate withdrawal transaction properly |  |  |  | The wrong amount was withdrawn. We selected 20 and it withdrew 40. Wrong amounts are being withdrawn |  |  |  |  | Manual Scripted Testing
15 | Withdrawal | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System verifies that it has sufficient cash on hand to fulfill the request | [8 empty] | Manual Scripted Testing
16 | Withdrawal | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System verifies that customer's balance is sufficient to fulfill the request | [8 empty] | Manual Scripted Testing
17 | Withdrawal | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | A withdrawal transaction can be cancelled by the customer any time prior to choosing the dollar amount | [8 empty] | Manual Scripted Testing
18 | Withdrawal | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | A withdrawal transaction can be cancelled by the customer any time prior to choosing the dollar amount | [8 empty] | Manual Scripted Testing
19 | Deposit | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System asks customer to choose an account to deposit to | [8 empty] | Manual Scripted Testing
20 | Deposit | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System asks customer to enter a dollar amount to deposit | [8 empty] | Manual Scripted Testing
21 | Deposit | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System asks customer to insert an envelope | [8 empty] | Manual Scripted Testing
22 | Deposit | Group 1 | Group 1 | Group | 2024-02-04 | 1 | V1.0 | System performs a legitimate deposit transaction properly |  |  |  | Balance is incorrect. We started with 100 and deposited 100. It should show 200 but shows 190 |  |  |  |  | Manual Scripted Testing
23 | Deposit | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | A deposit transaction can be cancelled by the customer any time prior to inserting an envelope | [8 empty] | Manual Scripted Testing
24 | Deposit | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | A deposit transaction can be cancelled by the customer any time prior to inserting an envelope | [8 empty] | Manual Scripted Testing
25 | Deposit | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | A deposit transaction can be cancelled by the customer any time prior to inserting an envelope | [8 empty] | Manual Scripted Testing
26 | Transfer | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | System asks customer to choose an account to transfer from | [8 empty] | Manual Scripted Testing
27 | Transfer | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | System asks customer to choose an account to transfer to | [8 empty] | Manual Scripted Testing
28 | Transfer | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | System asks customer to enter a dollar amount to transfer | [8 empty] | Manual Scripted Testing
29 | Transfer | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | System performs a legitimate transfer transaction properly |  |  |  | It added the wrong amount but the numbers worked out for total (given the wrong value was added). We deposited 10 but it only deposited 9.50 (correctly) |  |  |  |  | Manual Scripted Testing
30 | Transfer | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | [9 empty] | Manual Scripted Testing
31 | Transfer | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | A transfer transaction can be cancelled by the customer any time prior to entering dollar amount | [8 empty] | Manual Scripted Testing
32 | Transfer | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | A transfer transaction can be cancelled by the customer any time prior to entering dollar amount | [8 empty] | Manual Scripted Testing
33 | Inquiry | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | System asks customer to choose an account to inquire about |  |  |  | Checking is shown but savings is not. Instead money market is shown and there is not a money market with this card |  |  |  |  | Manual Scripted Testing
34 | Inquiry | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | System performs a legitimate inquiry transaction properly | [8 empty] | Manual Scripted Testing
35 | Inquiry | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | An inquiry transaction can be cancelled by the customer any time prior to choosing an account | [8 empty] | Manual Scripted Testing
36 | Invalid PIN Extension | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | Customer is asked to reenter PIN | [8 empty] | Manual Scripted Testing
37 | Invalid PIN Extension | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | Correct re-entry of PIN is accepted |  |  |  | If incorrect the first time, you need to correctly enter it twice to actually log in |  |  |  |  | Manual Scripted Testing
38 | Invalid PIN Extension | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | Incorrect re-entry of PIN is not accepted | [8 empty] | Manual Scripted Testing
39 | Invalid PIN Extension | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | Correct re-entry of PIN on the second try is accepted |  |  |  | If incorrect the first time, you need to correctly enter it twice to actually log in |  |  |  |  | Manual Scripted Testing
40 | Invalid PIN Extension | Group 2 | Group 2 | Group | 2024-02-04 | 1 | V1.0 | Correct re-entry of PIN on the third try is accepted |  |  |  | It was on the fourth but it did not lock us on the 3rd time when we typed it correctly. Once again had to type it in correctly twice |  |  |  |  | Manual Scripted Testing